## Blank Schedule
Date
Day | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100 | 101 | 102 | 103 | 104 | 105 | 106 | 107 | 108 | 109 | 110 | 111 | 112 | 113 | 114 | 115 | 116 | 117 | 118 | 119 | 120 | 121 | 122 | 123 | 124 | 125 | 126 | 127 | 128 | 129 | 130 | 131 | 132 | 133 | 134 | 135 | 136 | 137 | 138 | 139 | 140 | 141 | 142 | 143 | 144 | 145 | 146 | 147 | 148 | 149 | 150 | 151 | 152 | 153 | 154 | 155 | 156 | 157 | 158 | 159 | 160 | 161 | 162 | 163 | 164 | 165 | 166 | 167 | 168 | 169 | 170 | 171 | 172 | 173 | 174 | 175 | 176 | 177 | 178 | 179 | 180 | 181 | 182 | 183 | 184 | 185 | 186 | 187 | 188 | 189 | 190 | 191 | 192 | 193 | 194 | 195 | 196 | 197 | 198 | 199 | 200 | 201 | 202 | 203 | 204 | 205 | 206 | 207 | 208 | 209 | 210 | 211 | 212 | 213 | 214 | 215 | 216 | 217 | 218 | 219 | 220 | 221 | 222 | 223 | 224 | 225 | 226 | 227 | 228 | 229 | 230 | 231 | 232 | 233 | 234 | 235 | 236 | 237 | 238 | 239 | 240 | 241 | 242 | 243 | 244 | 245 | 246 | 247 | 248 | 249 | 250 | 251 | 252 | 253 | 254 | 255
Week | 1 | 1 | 1 | 1 | 1 |  |  | 2 | 2 | 2 | 2 | 2 |  |  | 3 | 3 | 3 | 3 | 3 |  |  | 4 | 4 | 4 | 4 | 4 |  |  | 5 | 5 | 5 | 5 | 5 |  |  | 6 | 6 | 6 | 6 | 6 |  |  | 7 | 7 | 7 | 7 | 7 |  |  | 8 | 8 | 8 | 8 | 8 |  |  | 9 | 9 | 9 | 9 | 9 |  |  | 10 | 10 | 10 | 10 | 10 |  |  | 11 | [6 empty] | 12 | [6 empty] | 13 | [6 empty] | 14 | [6 empty] | 15 | [6 empty] | 16 | [6 empty] | 17 | [6 empty] | 18 | [6 empty] | 19 | [6 empty] | 20 | [6 empty] | 21 | [6 empty] | 22 | [6 empty] | 23 | [6 empty] | 24 | [6 empty] | 25 | [6 empty] | 26 | [6 empty] | 27 | [6 empty] | 28 | [6 empty] | 29 | [6 empty] | 30 | [6 empty] | 31 | [6 empty] | 32 | [6 empty] | 33 | [6 empty] | 34 | [6 empty] | 35 | [6 empty] | 36 | [6 empty] | 37
Permit / Plan
Excavation
Foundation
Utilities
Framing
Measure Stair
Roofing
Doors & Windows
Exterior Finish
Mechanical
Insulation
Sign Stair Quote
Drywall Stock
Drywall & Tape
Prime
Deliver Stair
Stair Install
Wood Flooring
Interior Trim
Paint / Stain
Carpet
Walk Thru
Closing
*This schedule template is provided by Designed Stairs as a curtesy.
Designed Stairs accepts no responsibility for it's use

## 14 week
Date | 1/2/1011
Day | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98
Week | 1 | 1 | 1 | 1 | 1 |  |  | 2 | 2 | 2 | 2 | 2 |  |  | 3 | 3 | 3 | 3 | 3 |  |  | 4 | 4 | 4 | 4 | 4 |  |  | 5 | 5 | 5 | 5 | 5 |  |  | 6 | 6 | 6 | 6 | 6 |  |  | 7 | 7 | 7 | 7 | 7 |  |  | 8 | 8 | 8 | 8 | 8 |  |  | 9 | 9 | 9 | 9 | 9 |  |  | 10 | 10 | 10 | 10 | 10 |  |  | 11 | 11 | 11 | 11 | 11 |  |  | 12 | 12 | 12 | 12 | 12 |  |  | 13 | 13 | 13 | 13 | 13 |  |  | 14 | 14 | 14 | 14 | 14
Permit / Plan | X | X | X | X | X
Excavation | [7 empty] | X | X | X | X | X
Foundation | [14 empty] | X | X | X | X | X
Utilities | [21 empty] | X | X | X | X | X
Framing | [21 empty] | X | X | X | X | X |  |  | X | X | X | X | X
Measure Stair | [28 empty] | X | X
Roofing | [35 empty] | X | X | X | X | X
Doors & Windows | [31 empty] | X | X
Exterior Finish | [42 empty] | X | X | X | X | X |  |  | X | X | X | X | X |  |  | X | X | X | X | X |  |  | X | X | X | X | X
Mechanical | [42 empty] | X | X | X | X | X |  |  | X | X | X | X | X
Insulation | [49 empty] | X | X | X | X | X
Sign Stair Quote
Drywall Stock | [49 empty] | X | X | X | X | X
Drywall & Tape | [56 empty] | X | X | X | X | X
Prime | [63 empty] | X | X | X | X | X
Deliver Stair
Stair Install
Wood Flooring | [70 empty] | X | X | X | X | X
Interior Trim | [70 empty] | X | X | X | X | X |  |  | X | X | X | X | X
Paint / Stain | [77 empty] | X | X | X | X | X |  |  | X | X | X | X | X
Carpet | [87 empty] | X | X |  |  | X | X
Walk Thru | [93 empty] | X | X
Closing | [95 empty] | X

## 16 week
Date | 2011-01-02
Day | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100 | 101 | 102 | 103 | 104 | 105 | 106 | 107 | 108 | 109 | 110
Week | 1 | 1 | 1 | 1 | 1 |  |  | 2 | 2 | 2 | 2 | 2 |  |  | 3 | 3 | 3 | 3 | 3 |  |  | 4 | 4 | 4 | 4 | 4 |  |  | 5 | 5 | 5 | 5 | 5 |  |  | 6 | 6 | 6 | 6 | 6 |  |  | 7 | 7 | 7 | 7 | 7 |  |  | 8 | 8 | 8 | 8 | 8 |  |  | 9 | 9 | 9 | 9 | 9 |  |  | 10 | 10 | 10 | 10 | 10 |  |  | 11 | 11 | 11 | 11 | 11 |  |  | 12 | 12 | 12 | 12 | 12 |  |  | 13 | 13 | 13 | 13 | 13 |  |  | 14 | 14 | 14 | 14 | 14 |  |  | 15 | 15 | 15 | 15 | 15 |  |  | 16 | 16 | 16 | 16 | 16
Permit / Plan | X | X | X | X | X
Excavation | [7 empty] | X | X | X | X | X
Foundation | [14 empty] | X | X | X | X | X
Utilities | [21 empty] | X | X | X | X | X
Framing | [21 empty] | X | X | X | X | X |  |  | X | X | X | X | X
Measure Stair | [28 empty] | X | X
Roofing | [35 empty] | X | X | X | X | X
Doors & Windows | [31 empty] | X | X
Exterior Finish | [42 empty] | X | X | X | X | X |  |  | X | X | X | X | X |  |  | X | X | X | X | X |  |  | X | X | X | X | X
Mechanical | [42 empty] | X | X | X | X | X |  |  | X | X | X | X | X
Insulation | [56 empty] | X | X | X | X | X
Sign Stair Quote
Drywall Stock | [56 empty] | X | X | X | X | X
Drywall & Tape | [63 empty] | X | X | X | X | X |  |  | X | X | X | X | X
Prime | [77 empty] | X | X | X | X | X
Deliver Stair
Stair Install | [84 empty] | X | X | X | X | X
Wood Flooring | [84 empty] | X | X | X | X | X
Interior Trim | [84 empty] | X | X | X | X | X |  |  | X | X | X | X | X
Paint / Stain | [91 empty] | X | X | X | X | X |  |  | X | X | X | X | X
Carpet | [98 empty] | X | X | X | X | X
Walk Thru | [105 empty] | X | X | X
Closing | [108 empty] | X | X

## 20 week
Date | 2011-01-02
Day | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100 | 101 | 102 | 103 | 104 | 105 | 106 | 107 | 108 | 109 | 110 | 111 | 112 | 113 | 114 | 115 | 116 | 117 | 118 | 119 | 120 | 121 | 122 | 123 | 124 | 125 | 126 | 127 | 128 | 129 | 130 | 131 | 132 | 133 | 134 | 135 | 136 | 137 | 138 | 139 | 140
Week | 1 | 1 | 1 | 1 | 1 |  |  | 2 | 2 | 2 | 2 | 2 |  |  | 3 | 3 | 3 | 3 | 3 |  |  | 4 | 4 | 4 | 4 | 4 |  |  | 5 | 5 | 5 | 5 | 5 |  |  | 6 | 6 | 6 | 6 | 6 |  |  | 7 | 7 | 7 | 7 | 7 |  |  | 8 | 8 | 8 | 8 | 8 |  |  | 9 | 9 | 9 | 9 | 9 |  |  | 10 | 10 | 10 | 10 | 10 |  |  | 11 | 11 | 11 | 11 | 11 |  |  | 12 | 12 | 12 | 12 | 12 |  |  | 13 | 13 | 13 | 13 | 13 |  |  | 14 | 14 | 14 | 14 | 14 |  |  | 15 | 15 | 15 | 15 | 15 |  |  | 16 | 16 | 16 | 16 | 16 |  |  | 17 | 17 | 17 | 17 | 17 |  |  | 18 | 18 | 18 | 18 | 18 |  |  | 19 | 19 | 19 | 19 | 19 |  |  | 20 | 20 | 20 | 20 | 20
Permit / Plan | X | X | X | X | X
Excavation | [7 empty] | X | X | X | X | X
Foundation | [14 empty] | X | X | X | X | X
Utilities | [21 empty] | X | X | X | X | X
Framing | [21 empty] | X | X | X | X | X |  |  | X | X | X | X | X |  |  | X | X | X | X | X
Measure Stair | [31 empty] | X | X
Roofing | [42 empty] | X | X | X | X | X
Doors & Windows | [38 empty] | X | X
Exterior Finish | [49 empty] | X | X | X | X | X |  |  | X | X | X | X | X |  |  | X | X | X | X | X |  |  | X | X | X | X | X
Mechanical | [49 empty] | X | X | X | X | X |  |  | X | X | X | X | X
Insulation | [63 empty] | X | X | X | X | X
Sign Stair Quote
Drywall Stock | [63 empty] | X | X | X | X | X
Drywall & Tape | [70 empty] | X | X | X | X | X |  |  | X | X | X | X | X |  |  | X | X | X | X | X
Prime | [91 empty] | X | X | X | X | X
Deliver Stair
Stair Install
Wood Flooring | [91 empty] | X | X | X | X | X
Interior Trim | [98 empty] | X | X | X | X | X |  |  | X | X | X | X | X |  |  | X | X | X | X | X
Paint / Stain | [112 empty] | X | X | X | X | X |  |  | X | X | X | X | X
Carpet | [122 empty] | X | X |  |  | X | X | X
Walk Thru | [129 empty] | X | X |  |  | X | X | X
Closing | [136 empty] | X | X

## 24 Week
Date | 2011-01-02
Day | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100 | 101 | 102 | 103 | 104 | 105 | 106 | 107 | 108 | 109 | 110 | 111 | 112 | 113 | 114 | 115 | 116 | 117 | 118 | 119 | 120 | 121 | 122 | 123 | 124 | 125 | 126 | 127 | 128 | 129 | 130 | 131 | 132 | 133 | 134 | 135 | 136 | 137 | 138 | 139 | 140 | 141 | 142 | 143 | 144 | 145 | 146 | 147 | 148 | 149 | 150 | 151 | 152 | 153 | 154 | 155 | 156 | 157 | 158 | 159 | 160 | 161 | 162 | 163 | 164 | 165 | 166 | 167 | 168
Week | 1 | 1 | 1 | 1 | 1 |  |  | 2 | 2 | 2 | 2 | 2 |  |  | 3 | 3 | 3 | 3 | 3 |  |  | 4 | 4 | 4 | 4 | 4 |  |  | 5 | 5 | 5 | 5 | 5 |  |  | 6 | 6 | 6 | 6 | 6 |  |  | 7 | 7 | 7 | 7 | 7 |  |  | 8 | 8 | 8 | 8 | 8 |  |  | 9 | 9 | 9 | 9 | 9 |  |  | 10 | 10 | 10 | 10 | 10 |  |  | 11 | 11 | 11 | 11 | 11 |  |  | 12 | 12 | 12 | 12 | 12 |  |  | 13 | 13 | 13 | 13 | 13 |  |  | 14 | 14 | 14 | 14 | 14 |  |  | 15 | 15 | 15 | 15 | 15 |  |  | 16 | 16 | 16 | 16 | 16 |  |  | 17 | 17 | 17 | 17 | 17 |  |  | 18 | 18 | 18 | 18 | 18 |  |  | 19 | 19 | 19 | 19 | 19 |  |  | 20 | 20 | 20 | 20 | 20 |  |  | 21 | 21 | 21 | 21 | 21 |  |  | 22 | 22 | 22 | 22 | 22 |  |  | 23 | 23 | 23 | 23 | 23 |  |  | 24 | 24 | 24 | 24 | 24
Permit / Plan | X | X | X | X | X
Excavation | [7 empty] | X | X | X | X | X
Foundation | [14 empty] | X | X | X | X | X
Utilities | [21 empty] | X | X | X | X | X
Framing | [21 empty] | X | X | X | X | X |  |  | X | X | X | X | X |  |  | X | X | X | X | X |  |  | X | X | X | X | X
Measure Stair | [38 empty] | X | X
Roofing | [49 empty] | X | X | X | X | X
Doors & Windows | [45 empty] | X | X
Exterior Finish | [56 empty] | X | X | X | X | X |  |  | X | X | X | X | X |  |  | X | X | X | X | X |  |  | X | X | X | X | X |  |  | X | X | X | X | X
Mechanical | [56 empty] | X | X | X | X | X |  |  | X | X | X | X | X |  |  | X | X | X | X | X
Insulation | [77 empty] | X | X | X | X | X
Sign Stair Quote
Drywall Stock | [77 empty] | X | X | X | X | X
Drywall & Tape | [84 empty] | X | X | X | X | X |  |  | X | X | X | X | X |  |  | X | X | X | X | X |  |  | X | X | X
Prime | [108 empty] | X | X |  |  | X | X | X | X | X
Deliver Stair
Stair Install
Wood Flooring | [112 empty] | X | X | X | X | X
Interior Trim | [119 empty] | X | X | X | X | X |  |  | X | X | X | X | X |  |  | X | X | X | X | X |  |  | X | X | X | X | X
Paint / Stain | [140 empty] | X | X | X | X | X |  |  | X | X | X | X | X
Carpet | [150 empty] | X | X |  |  | X | X | X
Walk Thru | [157 empty] | X | X |  |  | X | X | X
Closing | [164 empty] | X | X

## 28 week
Date | 2011-01-02
Day | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100 | 101 | 102 | 103 | 104 | 105 | 106 | 107 | 108 | 109 | 110 | 111 | 112 | 113 | 114 | 115 | 116 | 117 | 118 | 119 | 120 | 121 | 122 | 123 | 124 | 125 | 126 | 127 | 128 | 129 | 130 | 131 | 132 | 133 | 134 | 135 | 136 | 137 | 138 | 139 | 140 | 141 | 142 | 143 | 144 | 145 | 146 | 147 | 148 | 149 | 150 | 151 | 152 | 153 | 154 | 155 | 156 | 157 | 158 | 159 | 160 | 161 | 162 | 163 | 164 | 165 | 166 | 167 | 168 | 169 | 170 | 171 | 172 | 173 | 174 | 175 | 176 | 177 | 178 | 179 | 180 | 181 | 182 | 183 | 184 | 185 | 186 | 187 | 188 | 189 | 190 | 191 | 192 | 193 | 194 | 195 | 196
Week | 1 | 1 | 1 | 1 | 1 |  |  | 2 | 2 | 2 | 2 | 2 |  |  | 3 | 3 | 3 | 3 | 3 |  |  | 4 | 4 | 4 | 4 | 4 |  |  | 5 | 5 | 5 | 5 | 5 |  |  | 6 | 6 | 6 | 6 | 6 |  |  | 7 | 7 | 7 | 7 | 7 |  |  | 8 | 8 | 8 | 8 | 8 |  |  | 9 | 9 | 9 | 9 | 9 |  |  | 10 | 10 | 10 | 10 | 10 |  |  | 11 | 11 | 11 | 11 | 11 |  |  | 12 | 12 | 12 | 12 | 12 |  |  | 13 | 13 | 13 | 13 | 13 |  |  | 14 | 14 | 14 | 14 | 14 |  |  | 15 | 15 | 15 | 15 | 15 |  |  | 16 | 16 | 16 | 16 | 16 |  |  | 17 | 17 | 17 | 17 | 17 |  |  | 18 | 18 | 18 | 18 | 18 |  |  | 19 | 19 | 19 | 19 | 19 |  |  | 20 | 20 | 20 | 20 | 20 |  |  | 21 | 21 | 21 | 21 | 21 |  |  | 22 | 22 | 22 | 22 | 22 |  |  | 23 | 23 | 23 | 23 | 23 |  |  | 24 | 24 | 24 | 24 | 24 |  |  | 25 | 25 | 25 | 25 | 25 |  |  | 26 | 26 | 26 | 26 | 26 |  |  | 27 | 27 | 27 | 27 | 27 |  |  | 28 | 28 | 28 | 28 | 28
Permit / Plan | X | X | X | X | X
Excavation | [7 empty] | X | X | X | X | X |  |  | X | X | X | X | X
Foundation | [21 empty] | X | X | X | X | X |  |  | X | X | X | X | X
Utilities | [35 empty] | X | X | X | X | X
Framing | [35 empty] | X | X | X | X | X |  |  | X | X | X | X | X |  |  | X | X | X | X | X |  |  | X | X | X | X | X
Measure Stair | [52 empty] | X | X
Roofing | [63 empty] | X | X | X | X | X
Doors & Windows | [59 empty] | X | X
Exterior Finish | [70 empty] | X | X | X | X | X |  |  | X | X | X | X | X |  |  | X | X | X | X | X |  |  | X | X | X | X | X |  |  | X | X | X | X | X
Mechanical | [70 empty] | X | X | X | X | X |  |  | X | X | X | X | X |  |  | X | X | X | X | X
Insulation | [91 empty] | X | X | X | X | X
Sign Stair Quote
Drywall Stock | [91 empty] | X | X | X | X | X
Drywall & Tape | [98 empty] | X | X | X | X | X |  |  | X | X | X | X | X |  |  | X | X | X | X | X |  |  | X | X | X | X | X
Prime | [126 empty] | X | X | X | X | X |  |  | X | X | X
Deliver Stair
Stair Install
Wood Flooring | [133 empty] | X | X | X | X | X
Interior Trim | [140 empty] | X | X | X | X | X |  |  | X | X | X | X | X |  |  | X | X | X | X | X |  |  | X | X | X | X | X |  |  | X | X | X | X | X
Paint / Stain | [168 empty] | X | X | X | X | X |  |  | X | X | X | X | X
Carpet | [178 empty] | X | X |  |  | X | X | X
Walk Thru | [185 empty] | X | X |  |  | X | X | X
Closing | [192 empty] | X | X

## 32 week
Date | 2011-01-02
Day | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100 | 101 | 102 | 103 | 104 | 105 | 106 | 107 | 108 | 109 | 110 | 111 | 112 | 113 | 114 | 115 | 116 | 117 | 118 | 119 | 120 | 121 | 122 | 123 | 124 | 125 | 126 | 127 | 128 | 129 | 130 | 131 | 132 | 133 | 134 | 135 | 136 | 137 | 138 | 139 | 140 | 141 | 142 | 143 | 144 | 145 | 146 | 147 | 148 | 149 | 150 | 151 | 152 | 153 | 154 | 155 | 156 | 157 | 158 | 159 | 160 | 161 | 162 | 163 | 164 | 165 | 166 | 167 | 168 | 169 | 170 | 171 | 172 | 173 | 174 | 175 | 176 | 177 | 178 | 179 | 180 | 181 | 182 | 183 | 184 | 185 | 186 | 187 | 188 | 189 | 190 | 191 | 192 | 193 | 194 | 195 | 196 | 197 | 198 | 199 | 200 | 201 | 202 | 203 | 204 | 205 | 206 | 207 | 208 | 209 | 210 | 211 | 212 | 213 | 214 | 215 | 216 | 217 | 218 | 219 | 220 | 221 | 222 | 223 | 224
Week | 1 | 1 | 1 | 1 | 1 |  |  | 2 | 2 | 2 | 2 | 2 |  |  | 3 | 3 | 3 | 3 | 3 |  |  | 4 | 4 | 4 | 4 | 4 |  |  | 5 | 5 | 5 | 5 | 5 |  |  | 6 | 6 | 6 | 6 | 6 |  |  | 7 | 7 | 7 | 7 | 7 |  |  | 8 | 8 | 8 | 8 | 8 |  |  | 9 | 9 | 9 | 9 | 9 |  |  | 10 | 10 | 10 | 10 | 10 |  |  | 11 | 11 | 11 | 11 | 11 |  |  | 12 | 12 | 12 | 12 | 12 |  |  | 13 | 13 | 13 | 13 | 13 |  |  | 14 | 14 | 14 | 14 | 14 |  |  | 15 | 15 | 15 | 15 | 15 |  |  | 16 | 16 | 16 | 16 | 16 |  |  | 17 | 17 | 17 | 17 | 17 |  |  | 18 | 18 | 18 | 18 | 18 |  |  | 19 | 19 | 19 | 19 | 19 |  |  | 20 | 20 | 20 | 20 | 20 |  |  | 21 | 21 | 21 | 21 | 21 |  |  | 22 | 22 | 22 | 22 | 22 |  |  | 23 | 23 | 23 | 23 | 23 |  |  | 24 | 24 | 24 | 24 | 24 |  |  | 25 | 25 | 25 | 25 | 25 |  |  | 26 | 26 | 26 | 26 | 26 |  |  | 27 | 27 | 27 | 27 | 27 |  |  | 28 | 28 | 28 | 28 | 28 |  |  | 29 | 29 | 29 | 29 | 29 |  |  | 30 | 30 | 30 | 30 | 30 |  |  | 31 | 31 | 31 | 31 | 31 |  |  | 32 | 32 | 32 | 32 | 32
Permit / Plan | X | X | X | X | X |  |  | X | X | X | X | X
Excavation | [14 empty] | X | X | X | X | X |  |  | X | X | X | X | X
Foundation | [28 empty] | X | X | X | X | X |  |  | X | X | X | X | X
Utilities | [42 empty] | X | X | X | X | X
Framing | [42 empty] | X | X | X | X | X |  |  | X | X | X | X | X |  |  | X | X | X | X | X |  |  | X | X | X | X | X |  |  | X | X | X | X | X
Measure Stair | [59 empty] | X | X
Roofing | [77 empty] | X | X | X | X | X |  |  | X | X
Doors & Windows | [73 empty] | X | X
Exterior Finish | [84 empty] | X | X | X | X | X |  |  | X | X | X | X | X |  |  | X | X | X | X | X |  |  | X | X | X | X | X |  |  | X | X | X | X | X |  |  | X | X | X | X | X
Mechanical | [84 empty] | X | X | X | X | X |  |  | X | X | X | X | X |  |  | X | X | X | X | X |  |  | X | X | X | X | X
Insulation | [112 empty] | X | X | X | X | X
Sign Stair Quote
Drywall Stock | [112 empty] | X | X | X | X | X
Drywall & Tape | [119 empty] | X | X | X | X | X |  |  | X | X | X | X | X |  |  | X | X | X | X | X |  |  | X | X | X | X | X
Prime | [147 empty] | X | X | X | X | X |  |  | X | X | X
Deliver Stair
Stair Install
Wood Flooring | [154 empty] | X | X | X | X | X
Interior Trim | [161 empty] | X | X | X | X | X |  |  | X | X | X | X | X |  |  | X | X | X | X | X |  |  | X | X | X | X | X |  |  | X | X | X | X | X |  |  | X | X | X | X | X
Paint / Stain | [196 empty] | X | X | X | X | X |  |  | X | X | X | X | X
Carpet | [206 empty] | X | X |  |  | X | X | X
Walk Thru | [213 empty] | X | X |  |  | X | X | X
Closing | [220 empty] | X | X

## 36 week
Date | 2011-01-02
Day | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100 | 101 | 102 | 103 | 104 | 105 | 106 | 107 | 108 | 109 | 110 | 111 | 112 | 113 | 114 | 115 | 116 | 117 | 118 | 119 | 120 | 121 | 122 | 123 | 124 | 125 | 126 | 127 | 128 | 129 | 130 | 131 | 132 | 133 | 134 | 135 | 136 | 137 | 138 | 139 | 140 | 141 | 142 | 143 | 144 | 145 | 146 | 147 | 148 | 149 | 150 | 151 | 152 | 153 | 154 | 155 | 156 | 157 | 158 | 159 | 160 | 161 | 162 | 163 | 164 | 165 | 166 | 167 | 168 | 169 | 170 | 171 | 172 | 173 | 174 | 175 | 176 | 177 | 178 | 179 | 180 | 181 | 182 | 183 | 184 | 185 | 186 | 187 | 188 | 189 | 190 | 191 | 192 | 193 | 194 | 195 | 196 | 197 | 198 | 199 | 200 | 201 | 202 | 203 | 204 | 205 | 206 | 207 | 208 | 209 | 210 | 211 | 212 | 213 | 214 | 215 | 216 | 217 | 218 | 219 | 220 | 221 | 222 | 223 | 224 | 225 | 226 | 227 | 228 | 229 | 230 | 231 | 232 | 233 | 234 | 235 | 236 | 237 | 238 | 239 | 240 | 241 | 242 | 243 | 244 | 245 | 246 | 247 | 248 | 249 | 250 | 251 | 252
Week | 1 | 1 | 1 | 1 | 1 |  |  | 2 | 2 | 2 | 2 | 2 |  |  | 3 | 3 | 3 | 3 | 3 |  |  | 4 | 4 | 4 | 4 | 4 |  |  | 5 | 5 | 5 | 5 | 5 |  |  | 6 | 6 | 6 | 6 | 6 |  |  | 7 | 7 | 7 | 7 | 7 |  |  | 8 | 8 | 8 | 8 | 8 |  |  | 9 | 9 | 9 | 9 | 9 |  |  | 10 | 10 | 10 | 10 | 10 |  |  | 11 | 11 | 11 | 11 | 11 |  |  | 12 | 12 | 12 | 12 | 12 |  |  | 13 | 13 | 13 | 13 | 13 |  |  | 14 | 14 | 14 | 14 | 14 |  |  | 15 | 15 | 15 | 15 | 15 |  |  | 16 | 16 | 16 | 16 | 16 |  |  | 17 | 17 | 17 | 17 | 17 |  |  | 18 | 18 | 18 | 18 | 18 |  |  | 19 | 19 | 19 | 19 | 19 |  |  | 20 | 20 | 20 | 20 | 20 |  |  | 21 | 21 | 21 | 21 | 21 |  |  | 22 | 22 | 22 | 22 | 22 |  |  | 23 | 23 | 23 | 23 | 23 |  |  | 24 | 24 | 24 | 24 | 24 |  |  | 25 | 25 | 25 | 25 | 25 |  |  | 26 | 26 | 26 | 26 | 26 |  |  | 27 | 27 | 27 | 27 | 27 |  |  | 28 | 28 | 28 | 28 | 28 |  |  | 29 | 29 | 29 | 29 | 29 |  |  | 30 | 30 | 30 | 30 | 30 |  |  | 31 | 31 | 31 | 31 | 31 |  |  | 32 | 32 | 32 | 32 | 32 |  |  | 33 | 33 | 33 | 33 | 33 |  |  | 34 | 34 | 34 | 34 | 34 |  |  | 35 | 35 | 35 | 35 | 35 |  |  | 36 | 36 | 36 | 36 | 36
Permit / Plan | X | X | X | X | X |  |  | X | X | X | X | X
Excavation | [14 empty] | X | X | X | X | X |  |  | X | X | X | X | X
Foundation | [28 empty] | X | X | X | X | X |  |  | X | X | X | X | X
Utilities | [42 empty] | X | X | X | X | X
Framing | [42 empty] | X | X | X | X | X |  |  | X | X | X | X | X |  |  | X | X | X | X | X |  |  | X | X | X | X | X |  |  | X | X | X | X | X |  |  | X | X | X | X | X
Measure Stair | [66 empty] | X | X
Roofing | [84 empty] | X | X | X | X | X |  |  | X | X | X | X | X
Doors & Windows
Exterior Finish | [91 empty] | X | X | X | X | X |  |  | X | X | X | X | X |  |  | X | X | X | X | X |  |  | X | X | X | X | X |  |  | X | X | X | X | X |  |  | X | X | X | X | X |  |  | X | X | X | X | X
Mechanical | [91 empty] | X | X | X | X | X |  |  | X | X | X | X | X |  |  | X | X | X | X | X |  |  | X | X | X | X | X |  |  | X | X | X | X | X
Insulation | [126 empty] | X | X | X | X | X
Sign Stair Quote
Drywall Stock | [126 empty] | X | X | X | X | X
Drywall & Tape | [133 empty] | X | X | X | X | X |  |  | X | X | X | X | X |  |  | X | X | X | X | X |  |  | X | X | X | X | X |  |  | X | X | X | X | X
Prime | [168 empty] | X | X | X | X | X |  |  | X | X | X | X | X
Deliver Stair
Stair Install
Wood Flooring | [175 empty] | X | X | X | X | X
Interior Trim | [182 empty] | X | X | X | X | X |  |  | X | X | X | X | X |  |  | X | X | X | X | X |  |  | X | X | X | X | X |  |  | X | X | X | X | X |  |  | X | X | X | X | X |  |  | X | X | X | X | X
Paint / Stain | [224 empty] | X | X | X | X | X |  |  | X | X | X | X | X
Carpet | [234 empty] | X | X |  |  | X | X | X
Walk Thru | [241 empty] | X | X |  |  | X | X | X
Closing | [248 empty] | X | X